## Sheet1
Date | Task
2021-10-28 | work on bill genreation and finaization
2021-10-29 | RND on HRMS source and SMAS source to find issues
2021-10-30 | cross verify available diffrerent resource to identify code merjing issues as per disucussion with sir zahid
2021-11-01 | resolve salary sheet report issues
2021-11-02 | Complete oppening balance screen with new requirement of adeel discussing on evening meeting
2021-11-03 | working on salary history report
2021-11-04 | starting work on bill installment
2021-11-05 | work on bill installment 20%
2021-11-07 | work on bill installment 40%
2021-11-08 | work on bill reading 10%
2021-11-09 | work on bill reading 20%
2021-11-10 | make common screen for billing reports like other module for billing report print
2021-11-12 | working on billing allocation 50%
2021-11-13 | working on billing allocation 80%
2021-11-14 | working on billing de-allocation 80%
2021-11-15 | complete allocation and de-allocation 100%
2021-11-16 | installment cancellation 70%
2021-11-17 | meter allocation 30%
2021-11-19 | complete meter info 100%
2021-11-20 | work on meter bill print 50%
2021-11-22 | complete meter bill print 100%
2021-11-23 | work on bill rebat 40%
2021-11-24 | work on bill rebat finalize 50%
2021-11-25 | work on rebat cancellation 50%
2021-11-26 | work on rebat changes 40%
2021-11-27 | work on rebat changes 90%
2021-11-28 | work on meter receipt 50%
2021-11-29 | work on meter receipt 70%
2021-11-30 | work on receipt inquiry 40%
2021-12-01 | work on APEX quries
2021-12-02 | work on meter reading change 50%
2021-12-13 | working on documentation module
2021-12-14 | working on adding ptv_fee and advance payment
2021-12-15 | working on documentation module database
2021-12-16 | working on documentation module make area, layout pages or make controller
2021-12-17 | working on documentation module documents parameter doc_type 30%
2021-12-18 | working on documentation module documents parameter doc_type 60%
2021-12-20 | working on documentation module documents parameter doc_type 90%
2021-12-21 | working on documentation module documents parameter doc_type 100% and done testing save document 10%
2021-12-22 | working on documentation module save documents 50%
2021-12-28 | working on documentation module save documents 80%
2021-12-29 | working on documentation module save documents 100% and display document 10%
2021-12-30 | working on documentation module display documents 50%
2021-12-31 | working on documentation module display documents 100%